## PiS
Create professional Gantt charts in GanttPRO in a few clicks
PiS | [12 empty] | 2026-04-14 14:40
Color | WBS Number |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Budget | Actual cost | MSP UID | MSP ID | MSP UID | MSP ID | Created | Creator | Type | Project | Level
| 1 | Faza 1: Analiza i specifikacija zahtjeva |  |  | 2026-04-13 08:00 | 2026-04-24 08:00 |  | 0 | 63 | 119 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 2026-04-13 17:09 | Antonija K | project | PiS | 1
| 1.1 |  | Intervjui s organizatorima Street Food Festa (prikupljanje detaljnih potreba) | Petra, Antonija | 2026-04-13 08:00 | 2026-04-16 16:30 |  | 0 | 28 | 56 | 0 | Open | Medium |  |  | 0 | 0 |  |  |  |  | 2026-04-13 17:09 | Antonija K | task | PiS / Faza 1: Analiza i specifikacija zahtjeva | 2
| 1.2 |  | Definiranje funkcionalnih zahtjeva | Ivan, Antonija | 2026-04-17 08:00 | 2026-04-21 16:30 |  | 0 | 21 | 42 | 0 | Open | Medium |  | 1.1 | 0 | 0 |  |  |  |  | 2026-04-13 17:11 | Antonija K | task | PiS / Faza 1: Analiza i specifikacija zahtjeva | 2
| 1.3 |  | Izrada Use Case dijagrama i procesnih tijekova | Petra | 2026-04-22 08:00 | 2026-04-23 16:30 |  | 0 | 14 | 21 | 0 | Open | Medium |  | 1.2 | 0 | 0 |  |  |  |  | 2026-04-13 17:12 | Antonija K | task | PiS / Faza 1: Analiza i specifikacija zahtjeva | 2
| 1.4 |  | Odobrena specifikacija | Antonija | 2026-04-24 08:00 | 2026-04-24 08:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 1.3 | 0 | 0 |  |  |  |  | 2026-04-13 17:27 | Antonija K | milestone | PiS / Faza 1: Analiza i specifikacija zahtjeva | 2
| 2 | Faza 2: Dizajn sustava i baze podataka |  |  | 2026-04-24 08:00 | 2026-05-07 08:00 |  | 0 | 63 | 91 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 2026-04-13 17:12 | Antonija K | project | PiS | 1
| 2.1 |  | Projektiranje ER modela baze podataka (izlagači, financije, osoblje) | Ivan | 2026-04-24 08:00 | 2026-05-04 16:30 |  | 0 | 49 | 28 | 0 | Open | Medium |  | 1.4 | 0 | 0 |  |  |  |  | 2026-04-13 17:14 | Antonija K | task | PiS / Faza 2: Dizajn sustava i baze podataka | 2
| 2.2 |  | Dizajn korisničkog sučelja (UI) | Marin | 2026-04-24 08:00 | 2026-05-04 16:30 |  | 0 | 49 | 21 | 0 | Open | Medium |  | 1.4 | 0 | 0 |  |  |  |  | 2026-04-13 17:15 | Antonija K | task | PiS / Faza 2: Dizajn sustava i baze podataka | 2
| 2.3 |  | Definiranje arhitekture sustava | Ivan, Marin | 2026-05-05 08:00 | 2026-05-06 16:30 |  | 0 | 14 | 42 | 0 | Open | Medium |  | 2.1, 2.2 | 0 | 0 |  |  |  |  | 2026-04-13 17:15 | Antonija K | task | PiS / Faza 2: Dizajn sustava i baze podataka | 2
| 2.4 |  | Spreman dizajn | Antonija | 2026-05-07 08:00 | 2026-05-07 08:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 2.3 | 0 | 0 |  |  |  |  | 2026-04-13 17:30 | Antonija K | milestone | PiS / Faza 2: Dizajn sustava i baze podataka | 2
| 3 | Razvoj - Iteracija 1: Operativna baza |  |  | 2026-05-07 08:00 | 2026-06-05 08:00 |  | 0 | 147 | 161 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 2026-04-13 17:15 | Antonija K | project | PiS | 1
| 3.1 |  | Postavljanje okruženja i razvoj baze podataka | Ivan | 2026-05-07 08:00 | 2026-05-13 16:30 |  | 0 | 35 | 49 | 0 | Open | Medium |  | 2.4 | 0 | 0 |  |  |  |  | 2026-04-13 17:15 | Antonija K | task | PiS / Razvoj - Iteracija 1: Operativna baza | 2
| 3.2 |  | Razvoj API-ja za izlagače i lokacije | Ivan | 2026-05-14 08:00 | 2026-05-29 16:30 |  | 0 | 84 | 63 | 0 | Open | Medium |  | 3.1 | 0 | 0 |  |  |  |  | 2026-04-13 17:16 | Antonija K | task | PiS / Razvoj - Iteracija 1: Operativna baza | 2
| 3.3 |  | Programiranje ekrana za unos i pregled izlagača | Marin | 2026-05-14 08:00 | 2026-05-29 16:30 |  | 0 | 84 | 28 | 0 | Open | Medium |  | 3.1 | 0 | 0 |  |  |  |  | 2026-04-13 17:16 | Antonija K | task | PiS / Razvoj - Iteracija 1: Operativna baza | 2
| 3.4 |  | Testiranje prve verzije modula i popravljanje bugova | Ivan, Marin, Petra | 2026-06-01 08:00 | 2026-06-04 16:30 |  | 0 | 28 | 21 | 0 | Open | Medium |  | 3.2, 3.3 | 0 | 0 |  |  |  |  | 2026-04-13 18:08 | Antonija K | task | PiS / Razvoj - Iteracija 1: Operativna baza | 2
| 3.5 |  | Prototip izlagača gotov | Antonija | 2026-06-05 08:00 | 2026-06-05 08:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 3.4 | 0 | 0 |  |  |  |  | 2026-04-13 17:32 | Antonija K | milestone | PiS / Razvoj - Iteracija 1: Operativna baza | 2
| 4 | Razvoj - Iteracija 2: Financije i Osoblje |  |  | 2026-06-05 08:00 | 2026-06-25 16:30 |  | 0 | 105 | 112 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 2026-04-13 17:17 | Antonija K | project | PiS | 1
| 4.1 |  | Programiranje algoritama za financijsku analitiku i izvještaje | Ivan | 2026-06-05 08:00 | 2026-06-18 16:30 |  | 0 | 70 | 42 | 0 | Open | Medium |  | 3.5 | 0 | 0 |  |  |  |  | 2026-04-13 17:17 | Antonija K | task | PiS / Razvoj - Iteracija 2: Financije i Osoblje | 2
| 4.2 |  | Izrada sučelja za upravljanje timovima (fotografi, marketing) | Marin | 2026-06-05 08:00 | 2026-06-18 16:30 |  | 0 | 70 | 7 | 0 | Open | Medium |  | 3.5 | 0 | 0 |  |  |  |  | 2026-04-13 17:18 | Antonija K | task | PiS / Razvoj - Iteracija 2: Financije i Osoblje | 2
| 4.3 |  | Spajanje financija i analitike u glavni dashboard, testiranje dashboarda | Ivan, Marin, Antonija | 2026-06-19 08:00 | 2026-06-25 16:30 |  | 0 | 35 | 63 | 0 | Open | Medium |  | 4.1, 4.2 | 0 | 0 |  |  |  |  | 2026-04-13 17:35 | Antonija K | task | PiS / Razvoj - Iteracija 2: Financije i Osoblje | 2
| 5 | Testiranje i osiguranje kvalitete |  |  | 2026-06-26 08:00 | 2026-07-09 08:00 |  | 0 | 63 | 56 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 2026-04-13 17:18 | Antonija K | project | PiS | 1
| 5.1 |  | Detaljno testiranje cijelog sustava | Ivan, Marin | 2026-06-26 08:00 | 2026-07-02 16:30 |  | 0 | 35 | 7 | 0 | Open | Medium |  | 4.3 | 0 | 0 |  |  |  |  | 2026-04-13 17:18 | Antonija K | task | PiS / Testiranje i osiguranje kvalitete | 2
| 5.2 |  | Korisničko testiranje (UAT) s organizatorima u Širokom Brijegu | Antonija | 2026-07-03 08:00 | 2026-07-06 16:30 |  | 0 | 14 | 21 | 0 | Open | Medium |  | 5.1 | 0 | 0 |  |  |  |  | 2026-04-13 17:19 | Antonija K | task | PiS / Testiranje i osiguranje kvalitete | 2
| 5.3 |  | Finalne optimizacije na temelju povratnih informacija klijenta | Ivan, Marin | 2026-07-07 08:00 | 2026-07-08 16:30 |  | 0 | 14 | 28 | 0 | Open | Medium |  | 5.2 | 0 | 0 |  |  |  |  | 2026-04-13 17:38 | Antonija K | task | PiS / Testiranje i osiguranje kvalitete | 2
| 5.4 |  | Sustav spreman | Antonija | 2026-07-09 08:00 | 2026-07-09 08:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 5.3 | 0 | 0 |  |  |  |  | 2026-04-13 17:39 | Antonija K | milestone | PiS / Testiranje i osiguranje kvalitete | 2
| 6 | Implementacija i dokumentacija |  |  | 2026-07-09 08:00 | 2026-07-17 16:30 |  | 0 | 49 | 28 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 2026-04-13 17:19 | Antonija K | project | PiS | 1
| 6.1 |  | Finalizacija korisničkog priručnika i tehničke dokumentacije | Petra | 2026-07-09 08:00 | 2026-07-10 16:30 |  | 0 | 14 | 7 | 0 | Open | Medium |  | 5.4 | 0 | 0 |  |  |  |  | 2026-04-13 17:19 | Antonija K | task | PiS / Implementacija i dokumentacija | 2
| 6.2 |  | Obuka osoblja festivala za rad u novom sustavu | Marin, Antonija | 2026-07-13 08:00 | 2026-07-15 16:30 |  | 0 | 21 | 14 | 0 | Open | Medium |  | 6.1 | 0 | 0 |  |  |  |  | 2026-04-13 17:50 | Antonija K | task | PiS / Implementacija i dokumentacija | 2
| 6.3 |  | Finalni deploy | Ivan | 2026-07-16 08:00 | 2026-07-17 16:30 |  | 0 | 14 | 7 | 0 | Open | Medium |  | 6.2 | 0 | 0 |  |  |  |  | 2026-04-13 17:51 | Antonija K | task | PiS / Implementacija i dokumentacija | 2
This document has been created with the help of https://ganttpro.com online service